## Product backlog
Project | Kyosk Dispatch Metrics
Stake holders / Customers / Users | abc, xyz etc
Created By | Kennedy Owiro
Date/Tme | 2nd May 2022
Kyosk_DM_Epic_001 | User Story ID | Features/Title | User Story | Status | Acceptance Creteria
This implementation looks at updating the below dispatch metrics and making them configurable: 1. Delivery window target value | DWTV1 | Application should allow users can configure daily orders target (cumulative total of order values to be received for the specific day) | As the application User, I want to be able to configure my daily orders target. So that I can manage my orders well. | New
| DWTV2 | Allow users to configure the delivery window limit | As the application User, want to be able to to configure the delivery window limit. So that my my oders arrive on time. | New
| DWTV3 | The delivery window limits | The delivery window limits MUST sum up to the daily target value. | New
| DWTV4 | The front-end user apps should be updated to select the next available delivery window unless the user opts to select another delivery window. | As the application User, I want to be able to change the delivery window. So that I am not compromised by unforeseen circumstances. | New
| DWTV5 | The front-end user applications display of value amount < Ksh 30,000. | The front-end user applications displays value to window saturation once the value amount is less than Ksh 30,000. | New
| DWTV6 | The front-end user applications displays count down timer | The front-end user applications is also displaying a countdown timer to window expiry once the duration left is less than 45 min. | New
| DWTV7 | Once a delivery window has been hit | Once a delivery window has hit its order value limit, it is deactivated and the system automatically recommends the next available window. | New
2. Market Operations Time i.e. a. Delivery Window time | MOT_DWT1 | Duka's goods delivery range in hours | The Application provides time range in hours that a Duka can have goods delivered.
| MOT_DWT2 | Optimun delivery windows | At optimum, Kyosk has 3 delivery windows | New
| MOT_DWT3 | The logistics manager will be able to configure delivery windows per market. | As the logistics manager, I want to be able to configure delivery windows per market. So as to allow optimal delivery of orders per market. | New
| MOT_DWT4 | The end-user apps will only allow users to select delivery times as configured in the system | As a User, I want to be able to select delivery times as configured in the system. So that I dont miss on a preffered delivery time. | New
2. Market Operations Time i.e. b. Cut-off Time | MOT_COT1 | Orders placed are pushed to the delivery window after the immediate one. | The App pushes orders placed to the delivery window
| MOT_COT2 | This enables dispatchers to prepare and collate orders to be serviced in the next available dispatch window. | The App enables dispatchers to prepare and collate orders to be serviced in the next available dispatch window. | New
| MOT_COT3 | The Logistics manager will be able to configure the cut off time duration per window per service zone. | As the Logistics manager, I want to be able to configure the cut off time duration per window per service zone. | New
| MOT_COT4 | The end-user apps will deactivate the active window once the cut-off time is reached and default to the next window. | The end-user apps deactivates the active window once the cut-off time is reached and default to the next window. | New
2. Market Operations Time i.e. c. Dispatch time | MOT_DW1 | Time range in which dispatchers will dispatch orders for the immediate delivery window. | The App provides time range in which the dispatchers will dispatch orders for the immediate delivery window. | New
| MOT_DW2 | The Logistics Manager will be able to configure the dispatch window range per market. | As the Logistics Manager, I want to be able to configure the dispatch window range per market. | New
In addition to the above, this implementation also looks to update the orders window page to ensure visibility and tabulation per delivery window for improved monitoring. | OWU1 | Order window updates | The Applicaton's Order window updates to capture tabs and windows | New
| OWU2 | Date display | The Application displays the current date, under each display | New
| OWU3 | Delivery windows | The Application displays the current dispatch window with details on delivery window it is servicing with order statuses | New
Order status | OWU_Status1 | Received | The received tab has all the received orders with capability to move to processing. | New
| OWU_Status2 | Move order to processing | Once order is moved, the Order moves to the Processing tab | New
| OWU_Status3 | Processing | The processing tab has all orders currently being processed prior to being dispatched (pending orders) | New
| OWU_Status4 | Dispatched | Dispatched tab has all orders that have been dispatched and enroute with drivers at that time | New
| OWU_Status5 | Cancelled/Rescheduled | Cancelled/Rescheduled tab has orders that have been cancelled or rescheduled | New
| OWU_Status6 | Completed | The completed tab has orders that have been completed i.e. payment has been received. | New
Search | Search_001 | Searching | Users should be able to search for orders via Duka name and order code for a specific date range. | New

## Sprint Planning
Project | Dealmart.com
Stake holders / Customers / Users | abc, xyz etc
Created By | Kennedy Owiro
Epic_Dispatch_Metrics_01 | User Story ID | Features/Title | User Story | Story Points | Sprint
This implementation looks at updating the below dispatch metrics and making them configurable: 1. Delivery window target value | DWTV1 | Application should allow users can configure daily orders target (cumulative total of order values to be received for the specific day) | As the application User, I want to be able to configure my daily orders target. So that I can manage my orders well. | 8 | 1
| DWTV2 | Allow users to configure the delivery window limit | As the application User, want to be able to to configure the delivery window limit. So that my my oders arrive on time. | 3 | 1
| DWTV3 | The delivery window limits | The delivery window limits MUST sum up to the daily target value. | 5 | 1
| DWTV4 | The front-end user apps should be updated to select the next available delivery window unless the user opts to select another delivery window. | As the application User, I want to be able to change the delivery window. So that I am not compromised by unforeseen circumstances. | 5 | 1
| DWTV5 | The front-end user applications display of value amount < Ksh 30,000. | The front-end user applications displays value to window saturation once the value amount is less than Ksh 30,000. | 8 | 1
| DWTV6 | The front-end user applications displays count down timer | The front-end user applications is also displaying a countdown timer to window expiry once the duration left is less than 45 min. | 6 | 1
| DWTV7 | Once a delivery window has been hit | Once a delivery window has hit its order value limit, it is deactivated and the system automatically recommends the next available window. | 8 | 1
2. Market Operations Time i.e. a. Delivery Window time | MOT_DWT1 | Duka's goods delivery range in hours | The Application provides time range in hours that a Duka can have goods delivered. | 7 | 2
| MOT_DWT2 | Optimun delivery windows | At optimum, Kyosk has 3 delivery windows | 9 | 2
| MOT_DWT3 | The logistics manager will be able to configure delivery windows per market. | As the logistics manager, I want to be able to configure delivery windows per market. So as to allow optimal delivery of orders per market. | 3 | 2
| MOT_DWT4 | The end-user apps will only allow users to select delivery times as configured in the system | As a User, I want to be able to select delivery times as configured in the system. So that I dont miss on a preffered delivery time. | 4 | 2
2. Market Operations Time i.e. b. Cut-off Time | MOT_COT1 | Orders placed are pushed to the delivery window after the immediate one. | The App pushes orders placed to the delivery window | 5 | 3
| MOT_COT2 | This enables dispatchers to prepare and collate orders to be serviced in the next available dispatch window. | The App enables dispatchers to prepare and collate orders to be serviced in the next available dispatch window. | 6 | 3
| MOT_COT3 | The Logistics manager will be able to configure the cut off time duration per window per service zone. | As the Logistics manager, I want to be able to configure the cut off time duration per window per service zone. | 7 | 3
| MOT_COT4 | The end-user apps will deactivate the active window once the cut-off time is reached and default to the next window. | The end-user apps deactivates the active window once the cut-off time is reached and default to the next window. | 6 | 3
2. Market Operations Time i.e. c. Dispatch time | MOT_DW1 | Time range in which dispatchers will dispatch orders for the immediate delivery window. | The App provides time range in which the dispatchers will dispatch orders for the immediate delivery window. | 8 | 4
| MOT_DW2 | The Logistics Manager will be able to configure the dispatch window range per market. | As the Logistics Manager, I want to be able to configure the dispatch window range per market. | 4 | 4
In addition to the above, this implementation also looks to update the orders window page to ensure visibility and tabulation per delivery window for improved monitoring. | OWU1 | Order window updates | The Applicaton's Order window updates to capture tabs and windows | 9 | 5
| OWU2 | Date display | The Application displays the current date, under each display | 2 | 5
| OWU3 | Delivery windows | The Application displays the current dispatch window with details on delivery window it is servicing with order statuses | 4 | 5
Order status | OWU_Status1 | Received | The received tab has all the received orders with capability to move to processing. | 5 | 6
| OWU_Status2 | Move order to processing | Once order is moved, the Order moves to the Processing tab | 7 | 6
| OWU_Status3 | Processing | The processing tab has all orders currently being processed prior to being dispatched (pending orders) | 6 | 6
| OWU_Status4 | Dispatched | Dispatched tab has all orders that have been dispatched and enroute with drivers at that time | 8 | 6
| OWU_Status5 | Cancelled/Rescheduled | Cancelled/Rescheduled tab has orders that have been cancelled or rescheduled | 4 | 6
| OWU_Status6 | Completed | The completed tab has orders that have been completed i.e. payment has been received. | 9 | 6
Search | Search_001 | Searching | Users should be able to search for orders via Duka name and order code for a specific date range. | 8 | 7

## Test Cases
TCID | User Story ID | Feature/Title | User Story | Steps | Expected
TC_METRICS_OO1 | DWTV1 | Application should allow users can configure daily orders target (cumulative total of order values to be received for the specific day) | As the application User, I want to be able to configure my daily orders target. So that I can manage my orders well. | 1. Open application 2. Go to configuration page 3. configure daily orders target | User is able configure daily orders target
TC_METRICS_OO2 | DWTV2 | Allow users to configure the delivery window limit | As the application User, want to be able to to configure the delivery window limit. So that my my oders arrive on time. | 1. Open application 2. Go to configuration page 3. configure delivery window limit | User should be able to configure delivery window limit
TC_METRICS_OO3 | DWTV3 | The delivery window limits | The delivery window limits MUST sum up to the daily target value. | 1. Open application 2. Go to configuration page 3. Confirm that the delivery window limit sums up to the daily target value | The delivery window limits MUST sum up to the daily target value.
TC_METRICS_OO4 | DWTV4 | The front-end user apps should be updated to select the next available delivery window unless the user opts to select another delivery window. | As the application User, I want to be able to change the delivery window. So that I am not compromised by unforeseen circumstances. | 1. Open application 2. Go to configuration page 3. Change the delivery window | The User should be able to change the delivery window
TC_METRICS_OO5 | DWTV5 | The front-end user applications display of value amount < Ksh 30,000. | The front-end user applications displays value to window saturation once the value amount is less than Ksh 30,000. | 1. Open application 2. View windows display | The front-end user applications should display value to window saturation once the value amount is less than Ksh 30,000.
TC_METRICS_OO6 | DWTV6 | The front-end user applications displays count down timer | The front-end user applications is also displaying a countdown timer to window expiry once the duration left is less than 45 min. | 1. Open application 2. Go to the dashboard 3. View windows display | The front-end user applications should display a countdown timer to window expiry once the duration left is less than 45 min.
TC_METRICS_OO7 | DWTV7 | Once a delivery window has been hit | Once a delivery window has hit its order value limit, it is deactivated and the system automatically recommends the next available window. | 1. Open application 2. Go to the dashboard 3.Go to delivery window 4. View the order value limit | Once a delivery window has hit its order value limit, it is deactivated and the system automatically recommends the next available window.
TC_METRICS_OO8 | MOT_DWT1 | Duka's goods delivery range in hours | The Application provides time range in hours that a Duka can have goods delivered. | 1. Open application 2. Go to the dashboard 3. Move to delivery panel | The Application should provide time range in hours that a Duka can have goods delivered.
TC_METRICS_OO9 | MOT_DWT2 | Optimun delivery windows | At optimum, Kyosk has 3 delivery windows | 1. Open application 2. Go to the dashboard 3. Go to delivery window | The app should have 3 delivery windows
TC_METRICS_OO10 | MOT_DWT3 | The logistics manager will be able to configure delivery windows per market. | As the logistics manager, I want to be able to configure delivery windows per market. So as to allow optimal delivery of orders per market. | 1. Open application 2. Go to the dashboard 3. Go to delivery window 4. Configure delivery window per market | The logistics manager should be able to configure delivery windows per market.
TC_METRICS_OO11 | MOT_DWT4 | The end-user apps will only allow users to select delivery times as configured in the system | As a User, I want to be able to select delivery times as configured in the system. So that I dont miss on a preffered delivery time. | 1. Open application 2. Go to the dashboard 3. Go to delivery window 4. Select deleivery time | The User should be able to select delivery times as configured in the system.
TC_METRICS_OO12 | MOT_COT1 | Orders placed are pushed to the delivery window after the immediate one. | The App pushes orders placed to the delivery window | 1. Open application 2. Go to the dashboard 3. Move to delivery panel | The App should push orders placed to the delivery window
TC_METRICS_OO13 | MOT_COT2 | This enables dispatchers to prepare and collate orders to be serviced in the next available dispatch window. | The App enables dispatchers to prepare and collate orders to be serviced in the next available dispatch window. | 1. Open application 2. Go to the dashboard 3. Move to dispatch window | The App should enable dispatchers to prepare and collate orders to be serviced in the next available dispatch window.
TC_METRICS_OO14 | MOT_COT3 | The Logistics manager will be able to configure the cut off time duration per window per service zone. | As the Logistics manager, I want to be able to configure the cut off time duration per window per service zone. | 1. Open application 2. Go to configuration page 3. Change the delivery window 4. Configure the cut off time | The Logistics manager should be able to configure the cut off time duration per window per service zone.
TC_METRICS_OO15 | MOT_COT4 | The end-user apps will deactivate the active window once the cut-off time is reached and default to the next window. | The end-user apps deactivates the active window once the cut-off time is reached and default to the next window. | 1. Open application 2. Go to configuration page 3. Change the delivery window 4. Configure the cut off time | The end-user apps should deactivate the active window once the cut-off time is reached and default to the next window.
TC_METRICS_OO16 | MOT_DW1 | Time range in which dispatchers will dispatch orders for the immediate delivery window. | The App provides time range in which the dispatchers will dispatch orders for the immediate delivery window. | 1. Open application 2. Go to configuration page 3. Change the delivery window 4. Check time range for dispatching orders | Time range in which dispatchers will dispatch orders for the immediate delivery window.
TC_METRICS_OO17 | MOT_DW2 | The Logistics Manager will be able to configure the dispatch window range per market. | As the Logistics Manager, I want to be able to configure the dispatch window range per market. | 1. Open application 2. Go to configuration page 3. Change the delivery window 4. Configure time range for dispatching orders | The Logistics Manager will be able to configure the dispatch window range per market.
TC_METRICS_OO18 | OWU1 | Order window updates | The Applicaton's Order window updates to capture tabs and windows | The Applicaton Orders window updates to capture tabs and windows | The Applicaton's Order window updates to capture tabs and windows
TC_METRICS_OO19 | OWU2 | Date display | The Application displays the current date, under each display
TC_METRICS_OO20 | OWU3 | Delivery windows | The Application displays the current dispatch window with details on delivery window it is servicing with order statuses
TC_METRICS_OO21 | OWU_Status1 | Received | The received tab has all the received orders with capability to move to processing.
TC_METRICS_OO22 | OWU_Status2 | Move order to processing | Once order is moved, the Order moves to the Processing tab
TC_METRICS_OO23 | OWU_Status3 | Processing | The processing tab has all orders currently being processed prior to being dispatched (pending orders)
TC_METRICS_OO24 | OWU_Status4 | Dispatched | Dispatched tab has all orders that have been dispatched and enroute with drivers at that time
TC_METRICS_OO25 | OWU_Status5 | Cancelled/Rescheduled | Cancelled/Rescheduled tab has orders that have been cancelled or rescheduled
TC_METRICS_OO26 | OWU_Status6 | Completed | The completed tab has orders that have been completed i.e. payment has been received.
TC_METRICS_OO27 | Search_001 | Searching | Users should be able to search for orders via Duka name and order code for a specific date range.

## Test Scenarios
SNO | Req#ID | Scenarios | No of Test Cases
1 | 1 | Delivery window target value | 7
2 | 2 | Market Operations Time i.e. Delivery Window time | 4
3 | 3 | Market Operations Time i.e. Cut-off Time | 4
4 | 4 | Market Operations Time i.e. Dispatch time | 2
5 | 5 | Update the orders window page to ensure visibility and tabulation per delivery window for improved monitoring. | 3
6 | 6 | Order Status | 6
7 | 7 | Search | 1

## API_Test_Cases
TCID | Test Description | HTTP METHOD TYPE | URL | BODY | SUCCESS RESPONSE | STATUS CODE
1 | Get all users | GET | http://localhost:3000/users | N/A | Returns list of all users | 200
2 | Get Single user | GET | http://localhost:3000/users/1 | N/A | Returns specific user details | 200
3 | Post new user | POST | http://localhost:3000/users | { "name": "David", "Location": "France", "Phone": "8923489", "orders": [ "Maize", "Stationaries" ] } | { "name": "David", "Location": "France", "Phone": "8923489", "orders": [ "Maize", "Stationaries" ], "id": 5 } | 201
4 | Update User details | PUT | http://localhost:3000/users/5 | { "name": "David", "Location": "France", "Phone": "11111111111", "orders": [ "Maize", "Stationaries" ], "id": 5 } | { "name": "David", "Location": "France", "Phone": "11111111111", "orders": [ "Maize", "Stationaries" ], "id": 5 } | 200
5 | Delete User | DELETE | http://localhost:3000/users/5 | N/A | { } | 200